## Summary
Waste and Resource Recovery - Service Development Timeline
Development Phases
Start by entering the month & year of your new
collection contract & then follow the link to phase 1
|  | Phase | 2007-05-01 | Contract Start
|  | 1 | Consultation and Planning
|  | 2 | Prepare Tender Documents
|  | 3 | Tendering
|  | 4 | New Service Commissioning
|  | 5 | Monitoring and Review
Summary of Timeframes
Disclaimer
The Department of Environment and Conservation (NSW) has prepared a model process-timeline for the work of planning and commissioning waste and resource recovery services for councils. The timeline has been developed in conjunction with a Local Government Working Group to assist local Councils. The model is intended as a guide only and has been developed following consultation with stakeholders. It does not constitute legal advice. Users of the model do so at their own risk. The model will require customising to each Council's particular requirements. Councils should seek and rely on their own legal or other advice concerning waste and resource recovery service contracts. The Department accepts no responsibility for errors or omissions in the model, or for any loss or damage arising from the use of the model.
Copyright © Department of Environment and Conservation (NSW), | Department of Environment and Conservation (NSW)
May 2005 | Sustainability Programs Division
DEC 2005/142 | PO Box 644 Parramatta NSW 2124
ISBN 1 74137 314 X | Phone: 02 8837 6000
Email: improvedpractice@environment.nsw.gov.au
Consultation and Planning - 9 Months
Prepare Tender Documents - 3 Months
Tendering - 4 Months
New Service Commissioning - 8 Months before & 6 months post new service
Monitoring & Review
Ongoing
Total Time 2 Years

## 1 - Consultation & Planning
Phase 1 - Consultation & Planning
Suggested Order | Key Consideration | Duration | Timing - Month and Year | [8 empty] | Status |  |  |  | Resources & Tips
|  |  | 2005-05-01 | 2005-06-01 | 2005-07-01 | 2005-08-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | Completed | In Progress | N/A | Not Started
1 | Establish Waste Management Committee (WMC) | 2 months | [13 empty] | Establish Waste Management Committee (WMC) | bar: 2005-05-01 to 2005-06-01
| The Waste Management Committee may include a community representative, Councillor(s), Outdoor Staff, Waste Manager, Waste Educator and public relations or customer service staff. Consult with Senior staff for the constitution of the Committee. The Committee is a good opportunity to involve interested Councillors and gain their trust and support throughout the development of the new contract. It is also an important mechanism for guiding decisions throughout the process and assisting to deliver critical actions. | [14 empty] | Advertisements can be placed in local media to invite participation in the WMC. | bar: 2005-05-01 to 2005-06-01
Deliverables | bar: 2005-05-01 to 2005-06-01
| Waste Management Committee established & regular meeting times set. | [14 empty] | Track your progress, completion dates or add comments here | bar: 2005-05-01 to 2005-06-01
2 | Check Your Current Situation | 3 months | [13 empty] | Check Your Current Situation | bar: 2005-05-01 to 2005-07-01
| Compile a Status Report on your current situation. Include details of the current services, maps of collection zones and routes, numbers and types of vehicles, ownership of mobile bins and collected materials, waste and recycling reprocessing and disposal facilities, timing of reprocessing and disposal contracts, composition or contamination audits, identified hazards, current service costs, as well as Council's infrastructure and any leasing arrangements. Some of this information will form the basis of the comprehensive information required in the tendering phase. | [14 empty] | Take photographs of existing infrastructure and services. | bar: 2005-05-01 to 2005-07-01
Deliverables | bar: 2005-05-01 to 2005-07-01
Status Report completed. | bar: 2005-05-01 to 2005-07-01
3 | Conduct Trials of Collection Services (Optional) | 6 months | [13 empty] | Conduct Trials of Collection Services (Optional) | bar: 2005-06-01 to 2005-11-01
| Trials can yield great results. Select an area that one truck may service (around 350 premises) and trial your proposed service. Trials should run for at least 3 months, be supported by clear educational information and include evaluation such as pre and post trial surveys. | [14 empty] | You may wish to involve Councillors in the trial. | bar: 2005-06-01 to 2005-11-01
Deliverables | bar: 2005-06-01 to 2005-11-01
Trial objectives and task lists developed - incorporating education and evaluation. | bar: 2005-06-01 to 2005-11-01
Trial completed. | bar: 2005-06-01 to 2005-11-01
Evaluation complete and report prepared. | bar: 2005-06-01 to 2005-11-01
4 | Review Accuracy of Council's Rates Database | 6 months | [13 empty] | Review Accuracy of Council's Rates Database | bar: 2005-07-01 to 2005-12-01
| Prepare an accurate List of Addresses for Contractor or Council delivery of mobile bins. The list will also assist you at the tendering stage to provide accurate information on the number of premises. Data inaccuracies at the time of new service commissioning will slow down the delivery of new bins and may increase costs to Council. Confirm the type of reports that the Rates Section can provide you and make this the basis of your database if possible. You may want to undertake an audit of premises in the LGA or selected areas, such as multi-occupancy dwellings or housing estates, to ensure a high level of accuracy. A system also needs to be developed and implemented to keep the List of Addresses up to date. | [14 empty] | Be very clear about what you want your database to look like before you start. Cross check existing databases, such as Rates data and within the Waste Section, to identify the level of inconsistency. Compare rated addresses and postal address to find discrepancies - particularly for corner blocks. | bar: 2005-07-01 to 2005-12-01
Deliverables | bar: 2005-07-01 to 2005-12-01
Accurate List of Addresses prepared. | bar: 2005-07-01 to 2005-12-01
System in place to update the List of Addresses over time. | bar: 2005-07-01 to 2005-12-01
5 | Undertake Performance Review of Existing Services | 2 months | [13 empty] | Undertake Performance Review of Existing Services | bar: 2005-07-01 to 2005-08-01
| Reviewing the performance of existing services will help you identify key areas that can be improved as part of the new contract, as well as the aspects of the current service that are performing well. This information will also benchmark current performance and allow evaluation of the new contract. Consider including missed service levels, early start and other complaints, bin handling, complaint response times, contamination incidents and rejection of materials by reprocessing facilities. | [14 empty] | Involve your existing Contractor in this process. | bar: 2005-07-01 to 2005-08-01
Deliverables | bar: 2005-07-01 to 2005-08-01
Performance Review report completed. | bar: 2005-07-01 to 2005-08-01
6 | Undertake Community Attitudes Survey | 3 months | [13 empty] | Undertake Community Attitudes Survey | bar: 2005-07-01 to 2005-09-01
| The survey results will determine current levels of knowledge, community attitudes towards existing services, problem areas and expectations and service changes the community wants to see in the future. There are a number of survey techniques to choose from including phone surveys, face to face surveys, mail out with a reply paid return envelope, and focus groups. The results of this survey will assist in developing the Waste Management and Resource Recovery Strategy, and help identify likely options or changes for the new service. | [14 empty] | (1) Make sure to pilot your survey with about a dozen people first to iron out any problems. The DECCW Guide to Using Research in Sustainability Programs is a good guide to use. See link below. This publication also has a list of useful references on how to develop public attitude surveys. | bar: 2005-07-01 to 2005-09-01
| Deliverables | [14 empty] | Using Research in Sustainability Programs | bar: 2005-07-01 to 2005-09-01
Community Attitudes Survey Completed. | bar: 2005-07-01 to 2005-09-01
7 | Undertake Waste Audits | 3 months | [13 empty] | Undertake Waste Audits | bar: 2005-07-01 to 2005-09-01
| Audits are important benchmarking exercises for setting targets, measuring performance of new services, identifying areas where resource recovery performance can be improved and evaluating effectiveness of education programs. Kerbside audits should include all of the regular kerbside services such as garbage, dry recyclables and organics. The audit provides information on the composition of all streams, the recovery rate of recyclables and organics, contamination levels, important contaminants and differences between single and multi-occupancy premises. Audits of reprocessing facilities such as Material Recovery Facilities and collection vehicles also provide valuable information on contamination levels. | [14 empty] | (1) You should get accreditation training if you do the audit yourself. (2) Avoid school holidays and the Christmas period if you want a more representative result. (3) If you want to compare results with previous audits then undertake at the same time of the year to avoid seasonal variation. (4) Guidelines for Conducting Household Kerbside Residual Waste, Recycling and Organics Audits in NSW Local Government Areas- 2011 is available from NSW EPA website or click on link below. | bar: 2005-07-01 to 2005-09-01
| Deliverables | [14 empty] | Addendum 2010 | bar: 2005-07-01 to 2005-09-01
| Audit completed. | [14 empty] | Waste Audit Guidelines | bar: 2005-07-01 to 2005-09-01
8 | Research best-practice | 6 months | [13 empty] | Research best-practice | bar: 2005-07-01 to 2005-12-01
| The latest best-practice examples can be found by visiting the NSW EPA website, searching the internet, attending conferences, talking to colleagues, speaking to collection contractors, reading industry magazines and researching what is happening in other States and overseas. | [14 empty] | EPA has developed a number of reports on resource recovery systems to view these documents visit www.epa.nsw.gov.au/warr/PrefResourceRecovery. The NSW EPA Preferred Resource Recovery Practices by Local Councils 2012 is also available see link below. Other useful NSW EPA documents on food and garden organics services include, Co-Collection of Domestic Food Waste and Garden Organics in Australia (see link below) and TBL Assessment (Domestic) Food Organics Management (see links below). | bar: 2005-07-01 to 2005-12-01
Co-collected Food and Garden Organics in Australia | bar: 2005-07-01 to 2005-12-01
| Deliverables | [14 empty] | TBL Assessment Food Organics | bar: 2005-07-01 to 2005-12-01
| Brief report detailing findings completed. | [14 empty] | Refer to The Preferred Resource Recovery Practices by Local Councils August 2012 also available by calling (02) 8837 6000. | bar: 2005-07-01 to 2005-12-01
9 | Gather Data for Key Performance Indicators (KPI's) | 2 months | [13 empty] | Gather Data for Key Performance Indicators (KPI's) | bar: 2005-09-01 to 2005-10-01
| Key performance indicators will help you establish the performance of current services and allow you to set a benchmark by which to measure the new service. Include elements from Council's Management Plan that relate to efficiency (such as response time on complaints) and also waste management-related KPI's such as contamination, resource recovery rates, recycling yields, waste generation and diversion rates. | [14 empty] | Good Practice Performance Measures for Kerbside Recycling Systems (February 2004) can be downloaded from the DECCW website or use the link below. | bar: 2005-09-01 to 2005-10-01
Deliverables | bar: 2005-09-01 to 2005-10-01
| Develop list of key performance indicators. | [14 empty] | Good Practice Performance Measures | bar: 2005-09-01 to 2005-10-01
Compile and present data on the key performance indicators. | bar: 2005-09-01 to 2005-10-01
10 | Undertake Community Market-Test Survey | 2 months | [13 empty] | Undertake Community Market-Test Survey | bar: 2005-10-01 to 2005-11-01
| This Survey tests options under consideration for new services with the community. It could include service frequency, mobile bin sizes, range of services and pricing. | [14 empty] | Use pictures, cost estimates and environmental benefits to compare the various options. | bar: 2005-10-01 to 2005-11-01
Deliverables | bar: 2005-10-01 to 2005-11-01
Market-Test Survey completed and evaluated. | bar: 2005-10-01 to 2005-11-01
11 | Develop Waste Management & Resource Recovery Strategy | 4 months | [13 empty] | Develop Waste Management & Resource Recovery Strategy | bar: 2005-10-01 to 2006-01-01
| This Strategy should be developed in conjunction with the WMC and take account of the Community Attitude Survey responses. It should contain your Councils vision and objectives, key performance data and other relevant information from "Checking your current situation" and "Undertaking performance reviews of existing services". Constraints and Infrastructure requirements also need to be assessed. The Strategy guides decisions on collection systems, and identifies the materials that are best to collect separately. Ideally the Strategy should span a 5-7 year period. | [14 empty] | A number of good Waste Management Strategies exist. A quick search on the internet can provide you with good examples of Local Council strategies. The NSW State Government Waste Avoidance and Resource Recovery Strategy can be found on the NSW EPA website or follow the link below. Australian Council of Recyclers has developed an Industry Recycling Materials Specifications Manual featuring Kerbside Recycling Specifications for post consumer materials (available to ACOR members only). visit website www.acor.org.au | bar: 2005-10-01 to 2006-01-01
WARR strategy | bar: 2005-10-01 to 2006-01-01
Deliverables | bar: 2005-10-01 to 2006-01-01
Strategy developed and endorsed by Council. | bar: 2005-10-01 to 2006-01-01
12 | Occupational Health & Safety (OHS) | 4 months | [13 empty] | Occupational Health & Safety (OHS) | bar: 2005-10-01 to 2006-01-01
| It is important to undertake a Risk Assessment of the proposed new services and to investigate all OHS related issues. The Risk Assessment should also look at current start times and whether they are being complied with. This will involve working with the existing contractor or Council staff to identify problem areas. A review of early start complaints may help. The Code of Practice for Collection of Domestic Waste being developed by WorkCover NSW will assist you to undertake the Risk Assessment. The Waste Contractors and Recyclers Association of NSW may also be of assistance. | [14 empty] | WorkCover have released a Code of Practice for the Collection of Domestic Waste 2005. Go to the web site below. Information on relevant Acts can also be found here. | bar: 2005-10-01 to 2006-01-01
| Deliverables | [14 empty] | www.workcover.nsw.gov.au | bar: 2005-10-01 to 2006-01-01
| Risk Assessment completed. | [14 empty] | Waste Collection Code of Practice | bar: 2005-10-01 to 2006-01-01
13 | Develop Draft Community Education Strategy (CES) | 3 months | [13 empty] | Develop Draft Community Education Strategy | bar: 2005-11-01 to 2006-01-01
| Develop the CES after the Waste Management and Resource Recovery Strategy, spanning a similar time period. The CES should address 'key focus areas' in your community (eg; schools, media, businesses) and take a 2 stage approach. Stage 1 should address the new service start-up phase while Stage 2 addresses the ongoing education, promotion and enforcement issues. The WMC as well as local teachers and state-level environmental educationalists should be consulted in the development of the CES. Cross-reference this with National and State Environmental Education Strategies. | [14 empty] | NSW EA has a number of publications including Does your Project Make a Difference? (2004) and What We Need is a Community Education Project (2000), these are available on the DECCW website or see link below. For more information on community education based resources visit the DECCW Education for Sustainability Professional Learning Hub (see link below). UK WRAP have developed a number of useful resources on how to develop a recycling campaign and communication resources, visit www.wrap.org.uk | bar: 2005-11-01 to 2006-01-01
What we need is . . . a community education project | bar: 2005-11-01 to 2006-01-01
Education for Sustainability Professional Learning Hub | bar: 2005-11-01 to 2006-01-01
| Deliverables | [14 empty] | Does your project make a difference? | bar: 2005-11-01 to 2006-01-01
Community Education Strategy completed. | bar: 2005-11-01 to 2006-01-01
14 | Appoint a Probity Officer | 1 month | [13 empty] | Appoint a Probity Officer | bar: 2005-12-01
| Consider appointing a dedicated Probity Officer, such as a Council lawyer, external probity advisor or an internal officer independent of the process. The Probity Officer will ensure that proper procedures and policies are followed in the development and evaluation of tenders. | [14 empty] | A number of Corruption Prevention Publications are available at the ICAC website (www.icac.nsw.gov.au) including Taking the Whiff out of Waste: Guidelines for Managing Corruption Risks in the Waste Sector and Taking the Con out of Contracting. The Department of Local Government has published Tendering Guidelines for NSW Local Government (2009) go to www.dlg.nsw.gov.au or see link below. Regional Organisations of Councils sometimes employ Probity Officers who may assist in this area. | bar: 2005-12-01
| Deliverables | [14 empty] | Tendering Guidelines for Local Government | bar: 2005-12-01
Probity Officer appointed. | bar: 2005-12-01
15 | Develop Service Options | 2 months | [13 empty] | Develop Service Options | bar: 2005-12-01 to 2006-01-01
| Options for the different types of collection services need to be determined as a first stage towards the tendering process. Sound research and discussions with other Councils will greatly assist. | [14 empty] | Refer to NSW EPA publication The Preferred Resource Recovery Practices by Local Councils August 2012 available on the EPA website. | bar: 2005-12-01 to 2006-01-01
Deliverables | bar: 2005-12-01 to 2006-01-01
Service option list developed. | bar: 2005-12-01 to 2006-01-01
16 | Contractor Consultation | 2 months | [13 empty] | Contractor Consultation | bar: 2005-12-01 to 2006-01-01
| Prior to the tendering process, it can be very useful to consult with potential contractors to discuss various options under consideration. An open meeting could be held, involving the Probity Officer, where options are explained and the Contractors are invited to submit written responses. This process should be treated as a separate stand alone exercise and is not intended to form part of the tender process or any tendering consultation. | [14 empty] | (1) Invite several Contractors and issue them with notes beforehand. (2) Chat with the Waste Contractor's & Recyclers Association of NSW for more information. (3) Ensure the Probity Officer is involved or present at the meeting. | bar: 2005-12-01 to 2006-01-01
Deliverables | bar: 2005-12-01 to 2006-01-01
Contractor consultation completed. | bar: 2005-12-01 to 2006-01-01
17 | Customer Service Review | 2 months | [13 empty] | Customer Service Review | bar: 2005-12-01 to 2006-01-01
| Review existing customer service functions including call centre staffing, number of phone lines, complaint management, and systems in place to monitor and report complaint levels. Staff feedback will assist the review. | [14 empty] | Gain feedback from staff who are also residents, and discuss with Line Managers and Directors. | bar: 2005-12-01 to 2006-01-01
Deliverables | bar: 2005-12-01 to 2006-01-01
Customer Service Review completed. | bar: 2005-12-01 to 2006-01-01
18 | Submit preferred approach to Council | 2 months | [13 empty] | Submit preferred approach to Council | bar: 2005-12-01 to 2006-01-01
| All of the above information should be compiled into a concise report for Council to consider and adopt. The Draft Waste Management and Resource Recovery Strategy can be submitted for adoption at this stage as well. At this stage you may still have a couple of preferred options that need to be tested in the tendering process. It is advisable to take along the mobile bin(s) (colours, sizes etc) under consideration and present technical as well as environmental and community findings to support the recommended services. | [14 empty] | Brief interested Councillors beforehand to ensure success. | bar: 2005-12-01 to 2006-01-01
Deliverables | bar: 2005-12-01 to 2006-01-01
Council report prepared and adopted by Council. | bar: 2005-12-01 to 2006-01-01
19 | Consider Expert Advice | 1 month | [13 empty] | Consider Expert Advice | bar: 2006-01-01
Consider whether to engage a consultant to help you through the tender development and/or evaluation process. | bar: 2006-01-01
Deliverables | bar: 2006-01-01
Consultant appointed (if required). | bar: 2006-01-01

## 2 - Prepare Tender Document
Phase 2 - Prepare Tender Documents
Suggested Order | Key Consideration | Duration | Timing - Month & Year |  |  | Status
|  |  | 2006-02-01 | 2006-03-01 | 2006-04-01 | Completed | In Progress | N/A | Not Started | Resources & Tips
1 | Establish Contract Committee | 1 month | [7 empty] | Establish Contract Committee
| A dedicated Contract Committee may be a Subcommittee of the Waste Management Committee formed in Phase 1 or it may include additional Council staff such as a purchasing or finance expert and/or an external/independent resource. Due to confidentiality issues it would not be advisable to have community representation. | [8 empty] | Confidentiality Agreements should be obtained from the Committee members.
Deliverables
Contract Committee established.
2 | Check/ Review Council's Tendering Procedures | 1 month | [7 empty] | Check/ Review Council's Tendering Procedures
| Different Councils have different tendering requirements. There may be local purchasing policies or similar that can affect the tendering process. If in doubt, check with your Procurement Officer. | [8 empty] | Liaise with the relevant officer responsible for tendering procedures in your Council.
Deliverables
Council's tendering requirements reviewed.
3 | Read the Legislation and appropriate guidelines | 1 month | [7 empty] | Read the Legislation and appropriate guidelines
| Ensure that you review and comply with the tendering requirements under the Local Government Act (1993). | [8 empty] | Go to the NSW Government legislation website below. Also visit the Department of Local Government's website (www.dlg.nsw.gov.au) for Tendering Guidelines for NSW Local Government 2009.
| Deliverables | [8 empty] | www.legislation.nsw.gov.au
| Tendering requirements under the Local Government Act reviewed. | [8 empty] | Tendering Guidelines
4 | Review and Adapt NSW EPA Model Collection Contracts | 3 months | [7 empty] | Review and Adapt NSW EPA Model Collection Contracts
| Model Waste and Recycling Collection Contracts are available from the DEC including Information for Tenderers, Conditions of Tendering, Conditions of Contract, Specifications, Tender Return Schedules, List of Attachments and Sample Advertisement. The accompanying Council User Guide will show you how to adapt the model to your Council. A simple checklist is included in the Appendix. Some of the options in the Model are discussed below including education, contamination management and customer service & complaint rectification. | [8 empty] | The NSW EPA Model Waste and Recycling Collection Contract package is for download off the EPA website. See link below.
Deliverables
| Council User Guide read. | [8 empty] | Model Waste and Recycling Collection Contract
Model contract documents adapted.
5 | Compile Tender Supporting Information | 2 months | [7 empty] | Compile Tender Supporting Information
| A range of information needs to be compiled and included with the final tender. A detailed attachment list is included in Section G of the DEC Model Collection Contract. | [8 empty] | The NSW EPA Model Waste and Recycling Collection Contract package is available by downloading from the NSW EPA website. Go to Section G of the Model Collection Contract for the list of attachments.
Deliverables
Tender supporting information compiled.
6 | Customer Service & Complaints Management | 2 months | [7 empty] | Customer Service & Complaints Management
| The introduction of new collection services may also include the introduction of a new complaint management system. Decide whether Council or the Contractor will be responsible for customer service, and any changes needed to Council's current complaint management system. | [8 empty] | Review the two options in the Customer Service and Complaint Rectification Clause 8 in Section D-Part 1 General Specification of the NSW EPA Model Collection Contract.
Deliverables
Customer Service and Complaint Rectification clause reviewed.
Decision made on responsibility for Customer Service.
7 | Education and Promotion | 1 month | [7 empty] | Education and Promotion
| Decide who will be responsible for Education and Promotion in the new contract. Many collection contractors now undertake this work, as it is closely linked to performance monitoring and complaints handling. | [8 empty] | Review the four education options in the NSW EPA Model Collection Contract - In Section D- Part 1 General Specification Clause 19
Deliverables
Education options reviewed.
Decision made on suitable education option.
8 | Contamination Management | 2 months | [7 empty] | Contamination Management
| The introduction of a new resource recovery collection service may include improved contamination management. Decide who will be responsible for producing supporting materials, taking into consideration the education option chosen above. | [8 empty] | Review the Recyclables and/or Organics Specification of the NSW EPA Model Collection Contract - particularly the Contamination Management Clause.
Deliverables
Recyclables and/or Organics Specifications reviewed.
Decision made on responsibility for producing supporting materials.
9 | Review and Adapt Tender Evaluation Criteria | 1 month | [7 empty] | Review and Adapt Tender Evaluation Criteria
| Review the Evaluation Criteria in Section B- Conditions of tednering Clause 11 of the NSW EPA Model Collection Contract and amend to suit Council. Determine weightings for the evaluation criteria. | [8 empty] | Develop an Excel model to input scoring.
Deliverables
Evaluation Criteria reviewed and customised.
Weightings for evaluation criteria determined.
10 | Legal Review | 1 month | [7 empty] | Legal Review
It is advisable to obtain the assistance of a lawyer to review the documents.
Deliverables
Legal review finalised.
11 | Consider Tender Briefing | 1 month | [7 empty] | Consider Tender Briefing
| If you wish to have a Tender Briefing - put the date, time and place in the Conditions of Tendering. | [8 empty] | Most have this meeting half-way through the Tender period.
Deliverables
Decision on tender briefing made and details included in Conditions of Tendering.
12 | Service Roll-out Plan & Tasks | 2 months | [7 empty] | Service Roll-out Plan & Tasks
| Compile a timeline of tasks and responsibilities for both Council and the Contractor that will take you through the roll-out of the new service. Once the successful Contractor is chosen, sit down with them to fine-tune this list. | [8 empty] | Microsoft Project is a handy tool to use for this.
Deliverables
Service Roll-out Plan & Tasks completed.
13 | Compile Tender Documents | 1 month | [7 empty] | Compile Tender Documents
| All sections of the Tender documents and the supporting information should now be ready to compile. Remember to update the Table of Contents. | [8 empty] | Consider what price to sell the documents for - around $50 per set is standard.
Deliverables
Tender package compiled and ready.

## 3 - Tendering
Phase 3 - Tendering
Suggested Order | Key Consideration | Duration | Timing - Month & Year |  |  |  | Status
|  |  | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | Completed | In Progress | N/A | Not Started | Resources & Tips
1 | Advertise Tender | 2 months | [8 empty] | Advertise Tender
| The 'Call to Tender' should be advertised in a Sydney metropolitan daily newspaper and a local newspaper and/or relevant district newspaper. The tender period needs to be a minimum of 21 days but 5 to 6 weeks is recommended. | [9 empty] | A sample tender advertisement is included in the NSW EPA Model Collection Contracts, available on the NSW EPA website (www.epa.nsw.gov,.au). For National Newspapers allow at least 3 days to get your advertisement booked.
Deliverables
Tender has been advertised in accordance with the tendering requirements under the Local Government Act.
2 | Record who takes Tender Documents | 2 months | [8 empty] | Record who takes Tender Documents
| Organise a central collection point for Tender Documents at the Council. Give the responsible person a template to keep a record of whoever purchases the tender documents. | [9 empty] | Keep electronic and hard copy list of names.
Deliverables
List of purchasers of Tender Documents compiled.
3 | Pre-Tender meeting | [9 empty] | Pre-Tender meeting
| The meeting should be chaired by a Senior Officer and notes taken. Have your Probity Officer and lawyer present if possible. Don't try and answer all questions from the floor - take questions on notice and respond to all tenderers in writing. | 1 month | [8 empty] | Provide written answers to everyone who received Tender Documents, not only those present at the pre-tender meeting.
Deliverables
Pre-Tender meeting held (if desired).
4 | Close/Opening of Tenders | [9 empty] | Close/Opening of Tenders
| Your Council will have a Tender Box that needs to be opened under certain conditions. See your administration section for support, and review the tendering requirements under the Local Government Act. | 1 month | [8 empty] | Contact the relevant Council Officer well in advance.
Deliverables
Tenders are opened in accordance with tendering requirements under the Local Government Act.
5 | Display Tender List | 1 month | [8 empty] | Display Tender List
Display the Tender List where it can be readily seen by members of the public. The Tender List needs to specify the name of tenderers in apparent order based on the total cost of the contract.
Deliverables
Tender List displayed in accordance with tendering requirements under the Local Government Act.
6 | Preliminary Evaluation | 1 month | [8 empty] | Preliminary Evaluation
This is an initial evaluation of conformity (i.e. the Tender is Conforming).
Deliverables
Preliminary evaluation is completed.
7 | Evaluation | 1 month | [8 empty] | Evaluation
| Assess Tenders in accordance with the tender assessment criteria and the weightings developed in Phase 2. Financial assessments can confidentially be forwarded to each tenderer for verification. | [9 empty] | The financial evaluation can be completed on a Microsoft Excel spreadsheet.
Deliverables
Tenders evaluated in accordance with assessment criteria and weightings.
Short list the Tenderers.
8 | Interview Tenderers | 1 month | [8 empty] | Interview Tenderers
| The Contract Committee should conduct interviews with short-listed tenderers. Structure the interview to allow a brief presentation by the tenderer first, followed by questions. | [9 empty] | Send the questions out in advance and take minutes of the interviews. Request a hard copy of all presentations.
Deliverables
Interviews with short-listed tenderers complete.
9 | Final Evaluation & Report | 1 month | [8 empty] | Final Evaluation & Report
| Compile your final scores for each tenderer against the evaluation criteria and develop a recommendation for the report to Council. Allow time for the Probity Officer to review the evaluation report and develop their probity report. This may then have to go to the General Manager. | [9 empty] | This often involves a presentation to Council and displaying any new service attributes such as mobile bins. Plan the timing of the Council meeting well in advance.
Deliverables
Evaluation complete.
Probity Officer report complete.
Report for Council meeting prepared.
Council Resolution.
10 | Advise Successful Tenderer | [9 empty] | Advise Successful Tenderer
| Advise the successful tenderer in writing. The letter will form part of the Contract. Use the Council resolution wording in your letter. | 1 month
Deliverables
Successful tenderers advised in writing.
11 | Advise Unsuccessful Tenderers | [9 empty] | Advise Unsuccessful Tenderers
| Advise the unsuccessful tenderers in writing and promptly return any deposits. | 1 month | [8 empty] | Consider offering feedback or a debriefing session with the Contract Committee and Probity Officer.
Deliverables
Unsuccessful tenderers advised in writing.
12 | Finalise and Sign Contract | [9 empty] | Finalise and Sign Contract
| Ensure that the appropriate Council staff and the Contractor sign all documentation. It is common to place signature initials on each page of the Contract Documents. | 1 month | [8 empty] | Have at least 3 copies of the final Contract.
Deliverables
Contract finalised and signed.
13 | Meet with Contractor to finalise Service Roll-Out Plan and tasks | 1 month | [8 empty] | Meet with Contractor to finalise Service Roll-Out
| Finalise Service Rollout Plan and any education tasks required of the Contractor. | [9 empty] | Roll-out Plan on Microsoft Project or similar can be useful.
Deliverables
Finalise Service Rollout Plan and tasks.

## 4 - New Service Commissioning
Phase 4 - New Service Commissioning
Suggested Order | Key Consideration | Duration | Timing Month & Year | [7 empty] | Timing Month & Year | [5 empty] | Status
|  |  | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | Completed | In Progress | N/A | Not Started | Resources & Tips
1 | Implement Roll-out Plan | 8 months | [18 empty] | Implement Roll-out Plan
| The Roll-out Plan is the logistical framework to track that all tasks are done on time by the responsible person. By now, the Roll-Out Plan has been refined with the assistance of the Contractor. | [19 empty] | Maintain constant contact with the Contractor to monitor progress.
Deliverables
Key milestones tracked and progress monitored.
2 | Contract Management Plan | 4 months | [18 empty] | Contract Management Plan
| A Contract Management Plan anticipates likely issues that will arise throughout the term of the Contract and identifies responsibilities, timeframes and appropriate management responses. | [19 empty] | Ensure you work closely with your new contractor and customer service staff so they also have ownership and input into the plan.
Deliverables
Contract Management Plan developed and agreed to by Council & the Contractor.
3 | Implement Community Education Plan | ongoing | [18 empty] | Implement Community Education Plan
| This plan may primarily be the responsibility of the Contractor or Council. The Plan should clearly detail the tasks to be undertaken, timeframes and responsibilities. | [19 empty] | A range of education resources are available on the DECCW website (see link to website below). Council case studies are also available on the NSW EPA website - use the link below. EPA has published a step-by-step guide on how to plan a community education project (see link below).
| Deliverables | [19 empty] | DECCW Sustainability education
| Community Education Plan completed. | [19 empty] | DECCW Sustainability education case studies
| Tasks regularly monitored. | [19 empty] | DECCW¦ What we need is . . . a community education project
4 | Check Equipment Requirements | 2 months | [18 empty] | Check Equipment Requirements
| Under some circumstances the Contractor provides all equipment, and under others the Council provides equipment. Check lead-times on equipment supply and ensure that logos, slogans and other information will be attached to equipment such as collection vehicles and mobile bins. Ensure that mobile bins and lifting devices on vehicles will be compatible. | [19 empty] | Issues may arise if the new bins are used by residents before the commencement of the new contract, especially if vehicles still in use have incompatible lifting devices.
Deliverables
Equipment requirements and lead times checked.
5 | Customer Service and Phones | ongoing | [18 empty] | Customer Service and Phones
| If Council will be responsible for customer service, then review the number of phone lines and customer service staff. The information gathered in Phase 1 will assist. Many Councils set up a telephone hotline to cope with the influx of calls. If the Contractor is responsible, keep informed of their progress and key milestones. | [19 empty] | Some phone systems cannot cope with a deluge of calls and you need to ensure the system in place is appropriate. It can take considerable time to get new phone lines or phone system so don't leave it too late.
Deliverables
Customer service and phone review completed and necessary action taken.
Progress regularly monitored.
6 | Staff and Customer Service Training | ongoing | [18 empty] | Staff and Customer Service Training
Develop a 'Questions and Answers' information sheet for staff and conduct training sessions. Additional information and training for customer service staff will need to be prepared as issues arise during the roll-out and commissioning.
Deliverables
Question and answer information sheets prepared.
Training schedule prepared and signed off by management.
Training undertaken.
7 | Updated List of Addresses | 2 months | [18 empty] | Updated List of Addresses
| The Contractor should be provided with an up-to-date and accurate List of Addresses that are to be serviced. Most mobile bin deliveries are recorded electronically so get your IT section to liaise with the Contractor on their required format. | [19 empty] | This information is commonly supplied in Microsoft Excel or Access.
Deliverables
Updated List of Addresses completed.
8 | Mobile Bin Distribution Plan | 2 months | [18 empty] | Mobile Bin Distribution Plan
It is important to develop a Mobile Bin Distribution Plan to assist in the mobile bin delivery and the retrieval and recycling of old bins. The Plan should be agreed to by Council and the Contractor undertaking the Bin roll-out. The development of the Bin Distribution Plan will need to include relevant staff from Council's Rates Department. The plan should address contingencies for when addresses do not appear on the List of Addresses, or where the number of domestic waste charges conflict with the number of services provided. Also remember that there are often differences between street addresses and rated addresses.
Deliverables
Mobile Bin Distribution Plan completed.
9 | Mobile Bin Delivery | 2 months | [18 empty] | Mobile Bin Delivery
| The delivery of the new mobile bins and the retrieval and recycling of old bins takes place several weeks before the actual service commencement date. It is important that the Education Package is attached to the mobile bins, and residents are advised of when the new service commences. Any discrepancies or delivery problems need to be dealt with promptly by the Contractor and Council, including the Rates Department. | [19 empty] | Bar-coding on mobile bins increases efficiency in delivery.
Deliverables
Mobile Bin Delivery complete.
10 | Commissioning Evaluation | 6 months | [18 empty] | Commissioning Evaluation
| Approximately 4 months after service commencement complete an evaluation of how Council and the Contractor both performed during the Commissioning Phase, including the accuracy of the Premises List and issues that arose during the roll-out. | [19 empty] | Keep a check list of positives and negatives during the mobile bin roll-out and the first few months of the new service. A positive outcome may be that the roll-out identifies additional rates revenue for Council from units or houses that have previously avoided paying rates or have been billed for the wrong number of services.
Deliverables
Commissioning evaluation complete.

## 5 - Monitoring & Review
Phase 5 - Monitoring & Review
Suggested Order | Key Consideration | Duration | Timing |  |  |  |  | Status |  |  |  | Resources & Tips
|  |  | 6-12 Months | 1-2 Years | 2-3 Years | 3-4 Years | 4-5 Years | Completed | In Progress | N/A | Not Started
1 | Contractor Performance | monthly | [9 empty] | Contractor Performance
| It is advisable to have regular monthly meetings with the Contractor to monitor progress on the delivery of the new service. The relevant Key Performance Indicators should be discussed at each meeting and a record kept of the key issues and actions required. Copies of the minutes should be sent to the Contractor following the meetings. | [10 empty] | You can use a Performance Management Committee for this function. Review the Performance Management Committee clause 18 in Section D- Part 1 General Specification of the NSW EPA Model Waste and Recycling Collection Contract.
2 | Community Education & Enforcement | ongoing | [9 empty] | Community Education & Enforcement
| The Community Education Program will change focus from 'introductory information' to ongoing education and enforcement. Release good news stories to the media from time-to-time. | [10 empty] | The Community Education Plan will have clear Actions, Responsibilities and Timeframes
3 | Reports to Council | quarterly | [9 empty] | Reports to Council
| Try and reserve a spot in the Council business paper to report service performance issues, particularly on resource recovery and waste diversion from landfill. | [10 empty] | Put reporting information into a template for ease of writing
4 | Contract Management Plan | ongoing | [9 empty] | Contract Management Plan
| Continually review and refine the plan. | [10 empty] | Make the plan work effectively and it will help with the development of the next Contract. Ensure you work closely with Customer Service staff including your new Contractor so that they have input and ownership of the plan.
5 | Service Performance Review | ongoing | [9 empty] | Service Performance Review
| Conduct a regular performance review with the Contractor to measure how they are going in relation to agreed performance measures and against benchmarks set out in the Contract. | [10 empty] | Give advance notice and an Agenda to the Contractor. Review the Performance Management Committee clause in the General Specification Section D- part 1 Clause 18 of the NSW EPA Model Waste and Recycling Collection Contract.